## Slide 1: Chapter 3 Determining Feasibility and Managing Analysis and Design Activities
Systems Analysis and Design
Kendall and Kendall
Fifth Edition

## Slide 2: Major Topics
Project initiation
Determining project feasibility
Project scheduling
Managing project activities
Manage systems analysis team members

## Slide 3: Project Initiation
Projects are initiated for two broad reasons:
  Problems that lend themselves to systems solutions
  Opportunities for improvement through
    Upgrading systems
    Altering systems
    Installing new systems

## Slide 4: Organizational Problems
Identify problems by
Check output against performance criteria
  Too many errors
  Work completed slowly
  Work done incorrectly
  Work done incompletely
  Work not done at all

## Slide 5: Organizational Problems
Observe behavior of employees
  High absenteeism
  High job dissatisfaction
  High job turnover

## Slide 6: Organizational Problems
Listen to feedback from vendors, customers, and suppliers
  Complaints
  Suggestions for improvement
  Loss of sales
  Lower sales

## Slide 7: Project Selection
Five specific criteria for project selection
  Backed by management
  Timed appropriately for commitment of resources
  It moves the business toward attainment of its goals
  Practicable
  Important enough to be considered over other projects

## Slide 8: Feasibility
A feasibility study assesses the operational, technical, and economic merits of the proposed project
There are three types of feasibility:
  Technical feasibility
  Economic feasibility
  Operational feasibility

## Slide 9: Technical Feasibility
Technical feasibility assesses whether the current technical resources are sufficient for the new system
If they are not available, can they be upgraded to provide the level of technology necessary for the new system

## Slide 10: Economic Feasibility
Economic feasibility determines whether the time and money are available to develop the system
Includes the purchase of
  New equipment
  Hardware
  Software

## Slide 11: Operational Feasibility
Operational feasibility determines if the human resources are available to operate the system once it has been installed
Users that do not want a new system may prevent it from becoming operationally feasible

## Slide 12: Activity Planning
Activity planning includes
  Selecting a systems analysis team
  Estimating time required to complete each task
  Scheduling the project
Two tools for project planning and control are Gantt charts and PERT diagrams

## Slide 13: Estimating Time
Project is broken down into phases
Further broken down into tasks or activities
Finally broken down into steps or even smaller units
Estimate time for each task or activity
May use a most likely, pessimistic, and optimistic estimates for time

## Slide 14: Gantt Charts
Easy to construct and use
Shows activities over a period of time

## Slide 15: Gantt Chart Example

## Slide 16: PERT Diagram
PERT - Program Evaluation and Review Technique
  PERT diagrams show precedence, activities that must be completed before the next activities may be started
  Used to calculate the critical path, the longest path through the activities
  This is the shortest time to complete the project

## Slide 17: PERT Diagram Example

## Slide 18: PERT Diagram Advantages
Easy identification of the order of precedence
Easy identification of the critical path and thus critical activities
Easy determination of slack time, the leeway to fall behind on noncritical paths